STOCKGURU Project Plan & Launch Milestones From Advanced Prototype to Production-Ready Platform ¦ March 2026

| Field | Detail |
| --- | --- |
| Document Type | Project Plan & Milestone Roadmap |
| Project | StockGuru — Real-Time Market Intelligence |
| Current Status | Advanced Prototype (Phase 2 Complete) |
| Target | Production-Ready SaaS Platform |
| Total Milestones | 5 Milestones across 4 Phases |
| Prepared For | Bharathi — Project Owner |
| Date | March 2026 |

# Table of Contents

# 1. Current State Assessment

Before defining the roadmap, it is essential to understand exactly where StockGuru stands today. The following table provides an honest, granular status of every major system component.

| Component | Status & Notes |
| --- | --- |
| 14-Agent orchestration pipeline | COMPLETE — All 14 agents implemented and coordinated in 15-min cycle |
| Market Scanner (60 stocks) | COMPLETE — Composite scoring, BUY/WATCH/HOLD/AVOID signals |
| Technical Analysis (IIFL-style) | COMPLETE — RSI, MACD, BB, EMAs, ATR, Pivot Points, Swing levels |
| News Sentiment (4 RSS feeds) | COMPLETE — Multi-source aggregation with LLM enhancement |
| Commodity/Crypto Agent | COMPLETE — 7 instruments tracked, sector impact mapped |
| Institutional Flow (FII/DII/PCR) | COMPLETE — Daily flows, market bias signals |
| Claude + Gemini LLM Brain | COMPLETE — Batched, cached, ~$2/month, fallback mode |
| Trade Signal Generator | COMPLETE — Entry/SL/T1/T2 with pivot-based zones |
| Sector Rotation Agent (30 sectors) | COMPLETE — Rotation signals, leader/laggard identification |
| Risk Manager (30 rules) | COMPLETE — Position sizing, VIX adjustment, sector limits |
| Paper Trading Engine | COMPLETE — Full Indian cost model, circuit breakers, 8-gate check |
| Morning Brief + Evening Debrief | COMPLETE — Telegram delivery at 8AM and 4PM IST |
| Pattern Memory & Learning | COMPLETE — SQLite persistence, win rate, pattern library |
| Earnings Calendar Agent | COMPLETE — Quarterly results schedule |
| Web Dashboard (10 tabs) | COMPLETE — Real-time AJAX, glassmorphism design |
| Telegram Alerts | COMPLETE — Bot notifications, inline HITL buttons |
| n8n Workflow Automation | COMPLETE — 15-min cycle, emergency alerts, morning brief |
| Railway Deployment | COMPLETE — Procfile, railway.json, environment config |
| Windows Launcher (START.bat) | COMPLETE — One-click local dev |
| Sovereign Layer (Phase 2) | MOSTLY COMPLETE — Debate Engine, HITL, Scryer, Post-Mortem built |
| IIFL API Live Data | PARTIAL — Configured but not fully validated end-to-end |
| Observer Agent (Option Chain) | PARTIAL — NSE scraping framework exists, needs testing |
| Synthetic Backtester | PARTIAL — Structure built, needs historical data integration |
| Automated Test Suite | BASIC — 4 test files, import/route/sovereign tests only |
| Database (PostgreSQL/production) | NOT BUILT — JSON files + SQLite (not scalable) |
| Multi-user Authentication | NOT BUILT — Single-user only |
| Performance Monitoring (Sentry/Prometheus) | NOT BUILT — No observability stack |
| Backtest Visual Charts | NOT BUILT — No historical chart visualization |
| Mobile App | NOT BUILT — Web dashboard only |
| API Rate Limiting & Security | NOT BUILT — No auth middleware on endpoints |

# 2. Gap Analysis — What Needs to Be Built

Based on the current state, the following gaps stand between StockGuru as an advanced prototype and a fully launched production platform. These have been grouped into priority tiers.

## 2.1 Critical Gaps (Block Launch)

- API Security: Flask routes are open — no authentication, rate limiting, or CORS hardening

- Production Database: JSON files are not crash-safe or scalable; need PostgreSQL migration

- Error Monitoring: No visibility when agents fail silently in production

- IIFL API Validation: Live data pipeline needs end-to-end testing before relied upon

- Test Coverage: Only ~10% code coverage — needs agent-level and integration tests

## 2.2 High-Priority Gaps (Launch Quality)

- Backtest Module: No ability to validate strategy on historical data before going live

- WebSocket Upgrade: Current 5-second AJAX polling creates unnecessary server load

- Enhanced Logging: Structured logging with rotation needed for production debugging

- Circuit Breaker UI: Sovereign War Room needs clearer visual states for VETO activation

- Observer Agent Completion: Option chain scraping needs hardening and testing

## 2.3 Medium-Priority Gaps (Growth Features)

- Multi-user Authentication: JWT-based auth to serve multiple users from Railway

- Watchlist Customization: Allow users to define their own stock universe beyond 60 stocks

- ML Score Adjustment: Replace some fixed-weight scoring with trained model (scikit-learn)

- WhatsApp Integration: n8n webhook for WhatsApp delivery (partially configured)

- Portfolio Analytics Dashboard: Deeper P&L analysis, drawdown charts, win-rate trends

## 2.4 Long-Term / Phase 4 Features

- React/Next.js Frontend: Replace vanilla JS SPA with component-based modern frontend

- Mobile App (React Native/Flutter): Native iOS/Android companion app

- Vector Memory (Qdrant): Upgrade agent_memory.db to semantic vector search

- Live Broker Integration: Secure, audited module with 2FA for actual trade execution

- Subscription SaaS Model: Payment integration, tiered feature access

# 3. Milestone Roadmap

The roadmap is organized into 5 milestones across 4 phases. Each milestone represents a meaningful, deployable improvement. Complete milestones in sequence — each one builds on the previous.

| Milestone | Focus & Timeline |
| --- | --- |
| M1 — Stabilize & Secure | Weeks 1–3: Fix critical gaps, secure API, improve test coverage |
| M2 — Complete & Polish | Weeks 4–6: Finish partial agents, add backtesting, WebSockets |
| M3 — Production Hardening | Weeks 7–10: PostgreSQL migration, observability, load testing |
| M4 — Growth Features | Weeks 11–16: Multi-user, ML scoring, mobile alerts, analytics |
| M5 — Platform Launch | Weeks 17–20: Public launch prep, SaaS model, React frontend |

MILESTONE 1 ¦ Weeks 1–3 ¦ Estimated Effort: 40–50 hours Stabilize & Secure

This milestone closes all critical gaps that would cause problems in a production environment. Nothing should be visible to end-users yet — this is infrastructure work.

### Objective: Make the existing system safe, stable, and testable

| Task / Deliverable | Effort | Priority | Status |
| --- | --- | --- | --- |
| Add API key authentication to all Flask routes (X-API-Key header middleware) | 6 hrs | Critical | Not Started |
| Implement rate limiting per endpoint (Flask-Limiter: 100 req/min/IP) | 3 hrs | Critical | Not Started |
| Harden CORS policy for production domain (whitelist Railway URL) | 2 hrs | Critical | Not Started |
| Validate IIFL API end-to-end: live price fetch → agent consumption → dashboard display | 8 hrs | Critical | Partial |
| Add structured logging (Python logging module with rotation, JSON format) | 4 hrs | Critical | Not Started |
| Write unit tests for all 14 agents (mock Yahoo Finance, mock LLM responses) | 16 hrs | Critical | Basic |
| Write integration test: full 15-min cycle end-to-end with fixture data | 6 hrs | High | Not Started |
| Add health check endpoint /api/health with agent status summary | 2 hrs | High | Not Started |
| Create .env.example with all required variables (remove real keys from .env) | 1 hr | High | Partial |
| Add agent crash recovery — isolated try/except per agent so one failure doesn't stop the cycle | 4 hrs | High | Partial |

### M1 Exit Criteria

- All Flask routes require authentication

- Agent-level tests pass with 80%+ coverage

- IIFL API data appears live on dashboard

- System runs 48+ hours without agent crash stopping the cycle

MILESTONE 2 ¦ Weeks 4–6 ¦ Estimated Effort: 50–60 hours Complete & Polish

This milestone completes all partial features and adds the most-requested enhancement: a backtest module. The goal is a system where everything shown to users is fully functional.

### Objective: Zero partial features — every agent and UI panel fully working

| Task / Deliverable | Effort | Priority | Status |
| --- | --- | --- | --- |
| Complete Observer Agent: validated NSE option chain scraping with error handling | 10 hrs | High | Partial |
| Complete Synthetic Backtester: integrate 2 years Yahoo Finance OHLCV, run 3 scenarios per signal | 14 hrs | High | Partial |
| Build backtest results UI panel (Dashboard Tab 11): charts with Chart.js, win rate by pattern | 8 hrs | High | Not Started |
| Upgrade AJAX polling to Flask-SocketIO WebSockets for zero-flicker live updates | 8 hrs | High | Not Started |
| Complete Debate Engine: 3-round Claude bull/bear/resolution flow with persistence to debate_log.json | 6 hrs | Medium | Partial |
| Sovereign War Room UI polish: visual VETO status, circuit breaker countdown, HITL queue display | 5 hrs | Medium | Partial |
| Add WhatsApp delivery via n8n webhook (partially configured in workflow JSON) | 3 hrs | Medium | Partial |
| Persistent alert history: store all past alerts in SQLite alerts_history.db | 4 hrs | Medium | Not Started |
| Dashboard mobile responsiveness audit and fix (currently optimized for desktop) | 4 hrs | Medium | Not Started |
| Update README.txt to full markdown README.md with architecture diagrams | 3 hrs | Low | Not Started |

### M2 Exit Criteria

- Observer Agent populating option chain data in Sovereign War Room

- Backtest panel showing historical performance of scanner signals

- WebSocket live updates working (no AJAX polling artifacts)

- Dashboard fully functional on mobile viewport

MILESTONE 3 ¦ Weeks 7–10 ¦ Estimated Effort: 60–70 hours Production Hardening

This milestone migrates from file-based storage to a production database, adds observability, and stress-tests the system for a multi-user environment. This is the final step before public launch.

### Objective: Production-grade infrastructure — database, monitoring, resilience

| Task / Deliverable | Effort | Priority | Status |
| --- | --- | --- | --- |
| Migrate JSON data files to PostgreSQL (Railway PostgreSQL add-on) | 16 hrs | Critical | Not Started |
| Migrate agent_memory.db schema to PostgreSQL with proper indexes | 6 hrs | Critical | Not Started |
| Add database connection pooling (SQLAlchemy + psycopg2) | 4 hrs | Critical | Not Started |
| Integrate Sentry for error tracking (Flask + Python SDK) | 3 hrs | High | Not Started |
| Add Prometheus metrics endpoint (/metrics) for Railway monitoring | 4 hrs | High | Not Started |
| Configure Railway auto-scaling rules based on CPU/memory metrics | 2 hrs | High | Not Started |
| Load test: simulate 10 concurrent users with Locust, identify bottlenecks | 6 hrs | High | Not Started |
| Add Redis caching for LLM responses (replace in-memory cache for multi-instance safety) | 8 hrs | High | Not Started |
| Implement database backup schedule (Railway PostgreSQL automated backups) | 2 hrs | High | Not Started |
| Security audit: OWASP checklist for Flask app, fix any vulnerabilities | 6 hrs | High | Not Started |
| Staging environment setup on Railway (separate from production) | 4 hrs | Medium | Not Started |
| CI/CD pipeline: GitHub Actions → run tests → deploy to Railway staging on PR | 8 hrs | Medium | Not Started |

### M3 Exit Criteria

- All data persisted in PostgreSQL — no JSON file dependency

- Sentry capturing errors in real-time

- System handles 10 concurrent users without degradation

- Zero-downtime deployment via Railway rolling update

- Staging environment mirrors production

MILESTONE 4 ¦ Weeks 11–16 ¦ Estimated Effort: 80–100 hours Growth Features

With a stable, production-grade foundation, this milestone adds the features that differentiate StockGuru in the market: multi-user support, AI-enhanced scoring, and richer analytics.

### Objective: Market-ready features for user acquisition and retention

| Task / Deliverable | Effort | Priority | Status |
| --- | --- | --- | --- |
| Multi-user authentication: JWT-based login, user profiles, per-user paper portfolios | 16 hrs | High | Not Started |
| User watchlist customization: CRUD API for personal stock universes (beyond 60 stocks) | 10 hrs | High | Not Started |
| ML scoring model: train RandomForest on signal_history.json to replace fixed-weight composite score | 14 hrs | High | Not Started |
| Portfolio analytics panel: drawdown chart, rolling win rate, expectancy trend, Sharpe ratio | 10 hrs | High | Not Started |
| Alert preferences: per-user Telegram chat ID, alert thresholds, sector filters | 6 hrs | Medium | Not Started |
| Stock detail deep-dive page: individual stock page with full OHLCV chart, agent analysis, news | 12 hrs | Medium | Not Started |
| Earnings calendar visual: calendar view with quarterly result dates, EPS estimates | 6 hrs | Medium | Not Started |
| Upgrade Memory Engine to Qdrant vector DB for semantic pattern search | 10 hrs | Medium | Not Started |
| Builder Agent activation: automatic dashboard panel proposals and safe auto-patching | 8 hrs | Low | Not Started |
| WhatsApp Business API integration (Twilio or WATI for premium alerts) | 6 hrs | Low | Not Started |

### M4 Exit Criteria

- 10+ different users can register, log in, and maintain separate paper portfolios

- ML model achieves higher signal precision than fixed-weight scoring (validated on holdout set)

- Portfolio analytics visible with 30+ days of paper trading history

- Each user can configure their own stock watchlist

MILESTONE 5 ¦ Weeks 17–20 ¦ Estimated Effort: 60–80 hours Platform Launch

The final milestone prepares StockGuru for public launch as a SaaS product. This includes the commercial infrastructure, marketing assets, and optionally a modern React frontend.

### Objective: Public launch — commercial, discoverable, monetizable

| Task / Deliverable | Effort | Priority | Status |
| --- | --- | --- | --- |
| SaaS pricing model: Free tier (3 signals/day, no Telegram) vs Pro tier (unlimited + alerts) | 4 hrs | High | Not Started |
| Payment integration: Razorpay (India) for Pro subscription billing | 10 hrs | High | Not Started |
| Landing page: marketing website with features, pricing, demo video, waitlist | 14 hrs | High | Not Started |
| Onboarding flow: guided setup wizard for API keys, Telegram bot, capital setting | 8 hrs | High | Not Started |
| SEBI compliance review: ensure all disclaimers are legally sound, no advice implied | 4 hrs | High | Not Started |
| Data privacy policy + Terms of Service (India IT Act compliance) | 4 hrs | High | Not Started |
| React/Next.js frontend (optional): modern component-based UI replacing vanilla JS SPA | 30 hrs | Medium | Not Started |
| Documentation portal: user guides, API reference, FAQ, video walkthroughs | 10 hrs | Medium | Not Started |
| Beta user program: invite 20 users, collect feedback, iterate for 2 weeks | 8 hrs | High | Not Started |
| Product Hunt / IndiaStartups.io launch campaign | 4 hrs | Medium | Not Started |

### M5 Exit Criteria

- 50 paid subscribers within 30 days of launch

- Payment processing live and working (Razorpay)

- Less than 0.1% system downtime in first month

- All SEBI disclaimer requirements met

- NPS (Net Promoter Score) from beta users ≥ 50

# 4. Timeline Summary

| Milestone | Duration ¦ Est. Hours ¦ Target Date |
| --- | --- |
| M1 — Stabilize & Secure | 3 weeks ¦ 40–50 hrs ¦ End of March 2026 |
| M2 — Complete & Polish | 3 weeks ¦ 50–60 hrs ¦ Mid April 2026 |
| M3 — Production Hardening | 4 weeks ¦ 60–70 hrs ¦ Mid May 2026 |
| M4 — Growth Features | 6 weeks ¦ 80–100 hrs ¦ End of June 2026 |
| M5 — Platform Launch | 4 weeks ¦ 60–80 hrs ¦ End of July 2026 |
| TOTAL | 20 weeks ¦ 290–360 hrs ¦ Q3 2026 Launch |

Note: Hours assume a solo developer working approximately 15–20 hours per week. With 2 developers, the timeline can be compressed to 12–14 weeks total.

# 5. New Technologies to Be Added

| Technology | Milestone ¦ Purpose |
| --- | --- |
| Flask-Limiter | M1 — API rate limiting |
| pytest + pytest-mock | M1 — Comprehensive test suite |
| Flask-SocketIO | M2 — WebSocket real-time updates |
| Chart.js (enhanced) | M2 — Backtest visualization charts |
| SQLAlchemy + psycopg2 | M3 — PostgreSQL ORM |
| Railway PostgreSQL | M3 — Production database |
| Redis (Railway add-on) | M3 — LLM cache, session storage |
| Sentry SDK | M3 — Error tracking |
| Prometheus + Grafana | M3 — Metrics and monitoring |
| Locust | M3 — Load testing |
| GitHub Actions | M3 — CI/CD automation |
| scikit-learn | M4 — ML scoring model |
| Qdrant | M4 — Vector memory engine |
| JWT (PyJWT) | M4 — User authentication |
| Razorpay SDK | M5 — Payment processing |
| Next.js / React | M5 — Modern frontend (optional) |

# 6. Risk Register

| Risk | Mitigation Strategy |
| --- | --- |
| Yahoo Finance API changes or rate limits | Add fallback to NSE direct API; implement request caching; monitor response changes |
| Claude API cost spike from heavy usage | LLM caching (10-min TTL), Gemini as primary for non-critical calls, budget alerts |
| IIFL API deprecation or authentication changes | Abstract data layer — all agents consume normalized price objects, not raw IIFL responses |
| Railway downtime or cost increase | Containerize with Docker for portability; evaluate AWS/GCP as fallback |
| SEBI regulatory action (being seen as investment advice) | Hardcode all disclaimers; paper-only enforcement; consult legal advisor before launch |
| Data corruption if server crashes during file write | PostgreSQL ACID transactions eliminate this risk (M3 priority) |
| Agent deadlock or infinite loop | Per-agent timeout enforcement (30-second limit); watchdog thread to restart hung agents |
| Low user adoption post-launch | Beta program in M5 to validate product-market fit before full spend on marketing |

# 7. Success Metrics for Launch

| Metric | Target at 3 Months Post-Launch |
| --- | --- |
| Registered users | 500+ |
| Paid Pro subscribers | 50+ |
| Signal win rate (paper trades) | ≥ 60% (backed by 90+ days pattern data) |
| System uptime | ≥ 99.5% |
| LLM cost per user per month | < ₹20 ($0.25) for Pro tier |
| Average session duration | ≥ 8 minutes on dashboard |
| Telegram alert open rate | ≥ 75% |
| NPS from beta users | ≥ 50 |
| P0 bugs in production | 0 |
| Mean time to recover (MTTR) | < 30 minutes |

Document prepared by Claude (Anthropic) for Bharathi | StockGuru Project Plan | March 2026